BBQ-Project

Stakeholders
1. Sponsor
2. Shop owners
3. Participants
4. Volunteers
5. FH-Kiel
6. Other (jealous) students
7. … (other less important stakeholders)

Goals
1. Avoid (heavily) injured participants
2. Let participants have fun (as far as possible)
3. … (more less important goals
Operational Goals
1. Execute all assessment plans in the risk related document to mitigate the risk of heavy injuries as far as possible
2. Provide all necessary equipment for a BBQ to provide a basis for having fun (as far as possible)
3. …

Material-List
1. Equipment
  1. Grills
  2. Coal
  3. Grill grate (Grillrost)
  4. Buckets (water)
  5. Plates (plastic or paper)
  6. Paper cups
  7. Spoons (plastic)
  8. Forks (plastic)
  9. Knifes (plastic)
  10. Umbrellas
  11. Tents
  12. First-Aid Kit
  13. Grill-Tongs
  14. Firestarter
  15. ...
2. Food
  1. Meat
    1. Pork (20%)
    2. Beef (30%)
    3. Chicken (30%)
    4. Sausages (mix 20%)
  2. Vegetarian food
    1. Vegetables
      1. Paprika
      2. Courgette (Zucchini)
      3. Aubergine
      4. Cucumber
      5. Field mushroom (Agaricus bisporus) (Champignon)
      6. Tomatoes
      7. ...
    2. Bread
    3. Buns
    4. Baguette
    5. Ketchup
    6. BBQ Sauces
    7. Butter
    8. Tofu
    9. ...
  3. Beverages
    1. Orange juice
    2. Apple juice
    3. Water
    4. …

Work Packages
1. Planning
  1. Prepare the cost calculation
  2. Participate in the doodle poll
  3. Organize a suitable location including seats and tables
  4. Organize change management to comply with Risk 10
  5. ...
2. Preparation
  1. Fetch all commodities listed in the “Material-List” under the point “Meat”
  2. Fetch all commodities listed in the “Material-List” under the point “Beverages”
  3. Fetch all commodities listed in the “Material-List” under the point “Vegetables”
  4. Fetch all commodities listed in the “Material-List” under the point “Vegetarian food” excluding the sub-point “Vegetables”
  5. Fetch all commodities listed in the “Material-List” under the point “Equipment”
    1. Fetch grills and grill grates
    2. Fetch coal and firestarter
    3. Fetch Buckets to comply to Risk 5
    4. Fetch plates, spoons, forks
    5. Fetch tents and / or umbrellas to comply with Risk 0
    6. Bring a first-aid kit to comply with Risk 4
    7. Bring grill tongs or forks to turn the grilled foods
    8. ...
  6. ...
3. Execution
  1. Take responsibility for providing first aid in cases of injuries
  2. Take responsibility for providing fire extinguishing measures in case of fires	breaking out
  3. Take responsibility for providing umbrellas or tents if the weather is rainy
  4. Take responsibility to emergency fetch food, if the number of participants exceeds the expectations beyond the safe limits (people starving)
  5. Grill requested foods
  6. Arrange tables, seats and food (setup location)
  7. ...