## Sheet1
Risk-classes:		Impact-classes:
high		high
medium		medium
low		low

Index	Name	Description	Probability	Impact	Mitigation / Assessment	Cost
0	Bad Weather	The weather is rainy and therefore not fit for usual BBQ	medium	high	Organize someone to bring umbrellas or a tent	?
1	Freezingly cold weather	A sudden fall of temperatures arises (maybe showers of snow)	low	medium	Inform people to bring their warm equipment and / adapt the BBQ to fit the temperature (e.g. add / Mulled whine without alcohol)	?
2	Allergies	Some people may have allergies against certain things	high	medium	Ask all food-providers too keep the information / about the foods components and ready-up to / provide it	?
3	BBQ Equipment not / Working	Some BBQ Equipment might be not working right away	medium	high	Organize someone to bring backup equipment	?
4	Injuries occur	somebody gets hurt during the BBQ	medium	medium	Assign someone responsible for first aid	?
5	A fire breaks out	Something catches fire during the BBQ	low	medium	Assign someone responsible for extinguishing / Possible fires (keep water and fire-extinguisher / ready)	?
6	Number of Participants / Is too low	The number of expected participants is lower than expected / And a lot of waist is produced	medium	low	Ask all participants to inform the project- / Management, if they can not come	?
7	Number of Participants / Is too high	The number of expected participants is higher than expected / And additional food needs to be fetched	high	high	Keep some money (10%) aside and assign someone / (someone with a vehicle) the responsibility of / Emergency fetching food in this case	?
8
9
10
11
12
13