## Sheet1
Risk-classes:		Impact-classes:		Budget:	500,00 €
high		high
medium		medium
low		low

Index	Name	Description	Probability	Impact	Mitigation / Assessment	Cost
0	Bad Weather	The weather is rainy and therefore not fit for usual BBQ	medium	high	Organize someone to bring umbrellas or a tent	?
1	Freezingly cold weather	A sudden fall of temperatures arises (maybe showers of snow)	low	medium	Inform people to bring their warm equipment and / adapt the BBQ to fit the temperature (e.g. add / Mulled whine without alcohol)	?
2	Allergies	Some people may have allergies against certain things	high	medium	Ask all food-providers too keep the information / about the food’s components and ready-up to / provide it	?
3	BBQ Equipment not / Working	Some BBQ Equipment might be not working right away	medium	high	Organize someone to bring backup equipment	?
4	Injuries occur	somebody gets hurt during the BBQ	medium	medium	Assign someone responsible for first aid	?
5	A fire breaks out	Something catches fire during the BBQ	low	medium	Assign someone responsible for extinguishing / Possible fires (keep water and fire-extinguisher / ready)	?
6	Number of Participants / Is too low	The number of expected participants is lower than expected / And a lot of waist is produced	medium	low	Ask all participants to inform the project- / Management, if they can not come	?
7	Number of Participants / Is too high	The number of expected participants is higher than expected / And additional food needs to be fetched	high	high	Keep some money (10%) aside and assign someone / (someone with a vehicle) the responsibility of / Emergency fetching food in this case	50,00 €
8	too optimistic estimates	Estimates in the calculation may be too low	high	high	To mitigate this risk, 30% are added to the / estimated costs	150,00 €
9	fetching wrong foods	Some types of food are ordered, even if nobody or almost / Nobody wants to eat it	medium	low	perform a survey to check the importance of items / Mentioned in the "Material-List"	?
10	not fetching wanted foods	Not providing foods, which would be highly appreciated by / Many participants	medium	medium	perform a survey to check the importance of items / Mentioned in the "Material-List" and ask all / Participants to mention foods, they would like to have, / Resulting in a doodle poll as a survey, managed by / Someone, who got assigned the responsibility for this / Task	?
11	…	remaining risks, not probable or important enough to get an / Own point			Keep some money (5%) aside to fix small possible / problems, if they should occur	25,00 €
12
13